CALL FOR PROPOSALS

Countering Violent Extremism through Community Dialogue Sessions and Small Grants Projects in Kismayo, Jubaland State

Ref :  SC0/025/01/2017

Rationale

With the evolving threat of violent extremism, policymakers and practitioners are focusing on preventing and countering radicalization and recruitment, and improving the resilience of individuals and communities against its appeal. This has been evidenced by a growing interest in countering violent extremism (CVE) programming by different actors. Likewise, States have become more attentive to the development of CVE strategies and are supporting initiatives that move beyond policy development and into implementation.

No one risk factor explains involvement in violent extremism.  Rather, it is the interaction of multiple risk factors that underpin the radicalization of individuals and communities ranging from economic and social disparities, lack of the rule of law, weak governance, corruption, widespread poverty and high unemployment rate amongst others.  With one of the youngest populations and still at its nascent stages of state building, Somalia faces an even greater challenge in meeting the needs of its youth. Unemployment rates are estimated at a staggering 67% among the 14-29 age brackets which combined with the presence of terrorist groups becomes a key contributor to youth radicalization and extremism. IOM recognizes that CVE initiatives cannot be undertaken by governments alone, rather, emphasis should be that communities and local partners need to be engaged to complement and enhance CVE efforts, as well as to strengthen community resilience against the threat.

To that end, IOM has conducted five 3-day Community Dialog Sessions for CVE in Kismayo throughout 2016. These dialogue sessions were interactive and participatory community consultations aimed towards joint problem identification and analysis and at reaching a common understanding and workable solutions. Ultimately, the 3-day sessions concluded with a number of proposed small grants projects that each community felt would contribute to CVE efforts. IOM is now seeking an Implementing Partner to coordinate and administer these small grants projects.

Objectives

IOM, through an implementing partner, intends to provide small and quick impact support that capitalizes on community driven interventions aimed at mitigating risk factors that contribute towards violent extremism.

More specifically, the small grants projects are aimed at:

- Engaging with the participants of the Community Dialogue Sessions to communicate and coordinate the project objectives and limitations.

- Installing 5 x solar-panel streetlights at each of the community locations in Kismayo, totaling 25 x solar-panel streetlights.

- Purchase and delivery of 15 x wheelchairs for disabled youth in each of the community locations in Kismayo, totaling 75 x wheelchairs.

- Facilitating a completion and handover ceremony with each of the 5 communities, emphasizing the relationship between the Community Dialogue Sessions for CVE and the subsequent Small Grants Projects.

Locations

In communication and coordination with the communities involved in the dialogue sessions and IOM, the small grants projects will be implemented in the following targeted locations in Kismayo, Jubaland State:

- Calanley Village

- Fanole Village

- Shagaalaha Village

- Farjano Village

- Guul-Wade Village

Scope of work

- Facilitate a meeting with Somali Family Services (the Implementing Partner for the Community Dialogue Sessions) and IOM to coordinate the small grants project activities and work plan.

- Meet with the local authorities to inform and gain acceptance of the small grants projects to be implemented, and to explain how they have followed on from the five community dialogue sessions in 2016.

- Engage with the respective participants of the Community Dialogue Sessions to communicate and coordinate the project objectives and limitations.

- In consultation and coordination with the respective communities and IOM, install 5 x soler-pannel streetlights at each of the community locations in Kismayo, totaling 25 x solar-panel streetlights.

  - The Implementing Partner, in consultation with the respective communities and IOM, will develop a fair and inclusive distribution proposal that aims to benefit the community as a whole.

- In consultation and coordination with the respective communities and IOM, purchase and distribute 15 x wheelchairs for disabled youth in each of the community locations in Kismayo, totaling 75 x wheelchairs.

  - The Implementing Partner, in consultation with the respective communities and IOM, will develop a fair and inclusive distribution proposal that considers aspects such as: gender; clan dynamics; disability profile; community youth profiles; etc.

- Facilitate a completion and handover ceremony with each of the 5 communities, emphasizing the relationship between the Community Dialogue Sessions for CVE and the subsequent Small Grants Projects.

  - The ceremonies should provide visibility for the Government of Japan as the project donor, and distribute the wheelchairs at the same time.

- Produce a brief post-meeting synopsis of the process, highlighting the achieved outputs and deliverables.

- Generate a report detailing key aspects of the completion and handover ceremonies.

- Work closely with IOM representatives during every stage of the contract period, providing regular updates on progress made.

- Produce an end of project final report, detailing all aspects of the implementation, challenges, lessons learned, and recommendations for further action.

Job requirements

The proposal needs to demonstrate how much experience and capacity (both physical and technical knowledge and expertise) the organization has on implementing similar interventions by explaining the:

- Number and outcomes of similar projects implemented i.e. experience with previous small grans projects.

- Methodologies of implementing similar activities.

### Eligibility Requirements for participating in this call for proposal

- They should be based in or operating within Somalia, preferably in Jubaland State.

- They should be legally registered in Somalia, and with the relevant regional authorities.

- They should have a working office in the areas and an organizational profile.

- They should have extensive working experience with similar interventions.

- They should have endorsement letters from the government, local authorities and international NGOs.

- They should have a good understanding and working relationships with the relevant line ministries, local authorities, local communities and/or international NGOs.

- They should have the financial capacity and adequate staff in relation to the required needs for the proposed project.

- They should have the financial capacity to pre-finance part of the activities.

What is the time frame of project implementation?

The project will be implemented in the five target areas of Kismayo, Jubaland State, over a period of no more than 1-month.

How to apply and where to send proposals?

Interested organizations are kindly requested to send a scanned copy of each of the documents listed above to the following email address: iomsomprocurement@iom.int  OR procurement@rmsomalia.org

Please ensure quotation of the reference number for this Call for Proposal

(SCO/025/01/2017)

Deadline for submission of proposals is: 31 Jan 2017

For more information on this project please send your queries to the below email;

iomsomalia@iom.int