## PRELIMINARIES
SECTION 1
PRELIMINARIES
SPECIAL NOTES
1 | The Contractor is required to check the numbers of the pages and should any be found to be missing or
in duplicate or the figures or writing indistinct, they must inform the Quantity Surveyors at once and have
the same rectified. Should the Contractor be in doubt about the precise meaning of any item, word or
figure, for any reason whatsoever, or observe any apparent omission of words or figures they must inform
the Quantity Surveyor in order that the correct meaning may be decided upon before the date for the
submission of the Tender.
2 | No liability whatever will be admitted nor claim allowed in respect of errors in the Contractor's Tender
due to mistakes in the Bills of Quantities which should have been rectified in the manner described
above.
3 | Any doubt or obscurity as to the meaning or intention of any part of the tender documents, or any
question arising, shall be taken up in writing, before submission of the tender so that the same can
be clarified.
4 | The Contractor shall not alter or otherwise qualify the text of these Bills of Quantities. Any alteration
or qualification made without authority will be ignored and the text of the Bills of Quantities as
printed will be adhered to.
5 | The Contractor shall be deemed to have made allowance in their prices generally to cover items of
Preliminaries or additions to Prime Cost Sums or other items, if these have not been priced against the
respective items.
6 | All items of measured work shall be priced in detail and tenders containing lump sums to cover trades or
groups of work must be broken down to show prices for each item before they will be accepted.
Lump sums to cover items of Preliminaries shall likewise be broken down if so required.
7 | In no case will any expenses incurred by Contractors in preparation of this Tender be reimbursed.
8 | The copyright of these Bills of Quantities is vested in the Quantity Surveyors and no part thereof may
be reproduced without their express permission given in writing.
9 | The Contractor is solely responsible for the accurate ordering of materials in accordance with the
Drawings and Architect's instructions and no claims for any loss or expense will be entertained for
orders for materials based upon the Bills of Quantities.
10 | The Bills of Quantities must be priced in US Dollar currency, i.e. US Dollars and Cents.
11 | The tender documents must be priced in ink.
INDEX
| SECTION NO. 1 |  |  | PRELIMINARIES AND GENERAL DESCRIPTIONS
| SECTION NO. 2 |  |  | PITCH
| SECTION NO. 3 |  |  | SPECTATOR STANDS 1
| SECTION NO. 4 |  |  | SPECTATOR STANDS 2
| SECTION NO. 4 |  |  | FENCE WALL
| SECTION NO. 5 |  |  | GRAND SUMMARY
ITEM | DESCRIPTION | [7 empty] | AMOUNT (US$)
SECTION NO. 1
PRELIMINARIES AND GENERAL DESCRIPTIONS
PRELIMINARY PARTICULARS
A | PARTIES
| The "Employer" is |  |  |  | INTERNATIONAL ORGANIZATION FOR MIGRATION
For the purpose of the works which are under the control of the consultants above, the
respective consultants shall be deemed to be invested with the duties and be representatives
of the Architect.
B | SITE
The site is located on BALCAD DISTRICT
The site of the works shall be used solely for the purpose of executing and completing the
Contract to the satisfaction of the Architect.
The Contractor shall obtain the Architect's approval for the siting of all temporary storage
areas for materials.
The Contractors shall visit the site to acquaint themselves with its nature and position, the
nature of the ground, sub- strata and other local conditions, position of power and water
supplies, access roads or any other limitations, and no claims for extras will be considered
on account of lack of knowledge in this respect.
The Contractor's attention is drawn to the fact that they shall confine themselves to the area
necessary for executing the works as instructed by the Architect.
The contractor must obtain the Architect's approval and directions regarding the use of any
materials found on the Site. Any such material utilized in the execution of the Contract shall be
measured and value assessed by the Quantity Surveyor and the amount credited to the
Employer.
[5 empty] | Carried To Collection |  |  | US$ | 0
GENERAL MATTERS
A | SUFFICIENCY OF TENDER
The Contractor shall be deemed to have satisfied themselves before tendering as to the
correctness and sufficiency of their Tender for the Works and of the rates and prices stated
in the priced Bills of Quantities, which rates and prices shall cover all their obligations under the
Contract and all matters and things necessary for the proper completion and maintenance of
the Works.
B | STAMP CHARGES
The Contractor shall allow for the payment of all Stamp Charges in connection with the Surety
Bond and Contract Agreement.
C | DEFINITIONS AND ABBREVIATIONS
Terms used in these Bills of Quantities shall be interpreted as follows:
| "Approved" |  | shall mean approved by the Architect.
| "as directed" |  | shall mean as directed by the Architect or any other consultant in the contract.
| "BS" |  | Shall mean the current British Standard Specification published by the British
Standards Institution, 2 Park Street, London W.1, England.
| "CM" |  | shall mean Cubic Meters.
| "SM" |  | shall mean Square Meters.
| "LM" |  | shall mean Linear Meters.
| "mm" |  | shall mean Millimeters.
| "Kg" |  | shall mean Kilograms.
| "No." |  | shall mean Number.
| "m.s" |  | shall mean Measured separately.
| "Ditto " |  | shall mean as described before or as above described.
D | PROGRESS SCHEDULE
The Contractor shall, upon receiving instructions to proceed with the work, draw up a Time
and Progress Schedule setting out the order in which the Works are to be carried out with the
appropriate dates thereof. This Time and Progress Schedule is to be agreed with the Architect
and no deviation from the order set out in this Schedule will be permitted without the written
consent of the Architect. The Main Contractor will be responsible for arranging the above
programme with all Sub-Contractors including the Nominated Sub-Contractors and Nominated
| Suppliers. | [7 empty] | 0
E | FIGURED DIMENSIONS
Figured dimensions are to be followed in preference to dimensions scaled from the Drawings;
but whenever possible dimensions are to be taken on the Site or from the Buildings. Before
any work is commenced by Sub-Contractors or Specialist Firms, dimensions must be checked
on the Site and/or buildings and agreed with the Contractor, irrespective of the comparable
dimensions shown on the Drawings. The Contractor shall be responsible for the accuracy of
such dimensions.
[5 empty] | Carried To Collection |  |  | US$ | 0
A | PROVISIONAL WORK
All "provisional" and other work liable to adjustment under this Contract shall be left uncovered
for a reasonable time to allow all measurements needed for such adjustment to be taken by
the Quantity Surveyor. Immediately the work is ready for measurement, the Contractor shall
give notice to the Quantity Surveyor.
If the Contractor makes default in these respects he shall, if the Architect so directs, uncover
the work at his own expense to enable the measurements to be taken.
B | EXISTING SERVICES
Prior to commencement of any work the Contractor is to ascertain from the relevant
Authorities the exact position, depth and level of all existing electric cables, water pipes or
other services in the area and they shall make whatever provisions may be required by the
Authorities concerned for the support and protection of such services. Any damage or
disturbance caused to any services shall be reported immediately to the Architect and the
relevant Authority and shall be made good to their satisfaction at the Contractor's expense.
C | TRANSPORT TO AND FROM THE SITE
The Contractor shall include in their prices for the transport of materials, workmen, etc., to and
from the Site of the proposed Works, at such hours and by such routes as are permitted by
the Authorities.
D | OVERTIME
The Contractor shall allow in their tender for any extra costs for overtime working they
consider will be necessary in order to complete the works by the contract Date of Completion.
If during the course of the Contract overtime is worked for a specific purpose in accordance
with a written instruction issued by the Architect, the Contractor will be reimbursed in respect
of such overtime to the extent only of the additional net cost of unproductive time payable
over and above the basic hourly rates as laid down by the Regulations of Wages and
Conditions of Employment Act, Building and Construction Industry Wages council and
excluding any bonuses, profits and overheads.
E | PUBLIC AND PRIVATE ROADS, PAVEMENTS, ETC.
The Contractor will be required to make good, at their own expense, any damage they may
cause to the present road surfaces and pavements within or beyond the boundary of the Site,
during the period of the Works. In particular, all existing trees, shrubs, plants, etc., which may
be destroyed or damaged during the progress of the Works are to be made good by the
Contractor to the approval of the Architect.
F | POLICE REGULATIONS
The Contractor is to allow for complying with all instructions and regulations of the
| Police Authorities. | [7 empty] | 0
[6 empty] | Carried To Collection |  | US$ | 0
A | CONTRACTORS' SUPERINTENDENCE
The Contractor shall constantly keep on the Works a literate English-speaking Agent or
Representative, competent and experienced in the kind of work involved, who shall give
his whole time to the superintendence of the Works. Such Agent or Representative shall
receive on behalf of the Contractor, directions and instructions from the Architect and such
directions and instructions shall be deemed given to the Contractor in accordance with the
Conditions of Contract. The Agent shall not be replaced without the specific approval of the
Architect.
It is to be a specific condition of this Contract that the successful Tenderer shall provide
on site throughout the period from the completion of the substructure to the Date for
Practical Completion a suitably qualified, experienced and competent person to ensure
that the works are carried out to the standard required by the specification and detailed
on the Drawings; and shall ensure that upon any termination of employment a suitable
replacement is found.
Before the Tenderer's offer is accepted the Architect will personally interview the Contractor's
proposed Representative. A curriculum vitae of past experience and qualifications must be
provided for the Architect's scrutiny.
The Architect's decision will be final regarding the suitability of the proposed Representative.
B | WATER
All water shall be fresh, clean and pure, free from earthy vegetable or organic matter, acid or
alkaline substance in solution or suspension.
The Contractor shall provide at their own risk and cost all water for use in connection with the
Works (including the work of Sub-Contractors). The Contractor shall provide at their own
expense all temporary distribution pipes, storage tanks, meters, etc., and they shall clear
| away same upon completion of the Works. | [7 empty] | 0
C | LIGHTING AND POWER
The Contractor shall provide at their own risk and cost all artificial lighting and power for use
on the Works, including all Sub-Contractors' and Specialists' requirements and including all
temporary connections, wiring, fittings, etc., and clearing away on completion. The Contractor
| shall pay all fees and obtain all permits in connection therewith. | [7 empty] | 0
D | SAFETY
In particular there shall be proper provision of planked footways and guard-rails to scaffolding,
etc.; protection against falling materials and tools and the Site shall be kept tidy and clear of
| dangerous rubbish. | [7 empty] | 0
The Architect shall be empowered to suspend work on the Site should he consider these
conditions are not being observed, and no claim arising from such a suspension will be allowed.
[5 empty] | Carried To Collection |  |  | US$ | 0
A | PROTECTIVE CLOTHING
The Contractor shall provide all protective or any other special clothing or equipment for their
employees that may be necessary.
These shall include, inter-alia, safety helmets, gloves, goggles, earmuffs, gumboots, steel
toed boots, overalls, etc according to the type of work. The Contractor shall ensure
| that all safety and protective gear are worn by all staff on site at all times | [7 empty] | 0
MATERIALS AND WORKMANSHIP
B | GENERALLY
All materials shall be new unless otherwise directed or permitted by the Architect and in all
cases where the quality of goods or materials is not described or otherwise specified, is to be
the best quality obtainable in the ordinary meaning of the word "best" and not merely a trade
signification of that word.
All materials and workmanship shall, unless otherwise specified or described, conform to the
appropriate Kenya Bureau of Standards or British Standards Institution Specification current
at the date of tender.
The Contractor shall order all materials to be obtained from overseas immediately after the
Contract is signed and shall also order materials to be obtained from local sources as early as
necessary to ensure that such materials are on Site when required for use in the Works.
The Contractor shall be responsible for and shall replace or make good at their own expense
any materials lost or damaged.
The Works throughout shall be executed by skilled workmen well versed in their respective
trades.
C | REJECTED WORKMANSHIP OR MATERIALS
Any workmanship or materials not complying with the specific requirements or approved
samples or which have been damaged, contaminated or have deteriorated, must immediately
be removed from the Site and replaced at the Contractor's expense, as required.
D | PROPRIETARY MATERIALS
Where proprietary materials are specified herein-after the Contractor may propose the use of
materials of other manufacture but equal quality for approval by the Architect.
All materials and goods, where specified to be obtained from a particular manufacturer or
supplier are to be used or fixed strictly in accordance with their instructions.
E | SAMPLES
The Contractor shall furnish at the earliest possible opportunity before work commences and
at his own cost, any samples of materials or workman-ship that may be called for by the
Architect for his approval or rejection, and any further samples in the case of rejection until
such samples are approved by the Architect and such samples, when approved, shall be the
| minimum standard for the work to which they apply. | [7 empty] | 0
[5 empty] | Carried To Collection |  |  | US$ | 0
A | CONCRETE TESTS
Concrete test cubes I.e. per set of three as later described, including testing fees, labour
and materials, making moulds, transport and handling etc.. and ensuing copies of tests
are promptly dispatched to the Architect's and Quantity Surveyor's offices.
| Successful tests only (Provisional) | [7 empty] | 0
TEMPORARY WORKS
B | SPACE AND SERVICES FOR THE ARCHITECT
The Contractor shall provide where directed within the site, site offices and clean toilet facilities
for the sole use of the Architect and their representatives to the satisfaction of the Local
Authorities. The offices shall be provided with adequate furniture and the contractor shall
provide the services of a sweeper, pay all charges and keep the facilities in a clean and
sanitary condition during the whole period of the Works. In particular, the Contractor is to
note that the station will continue with operations during the period of the works and a
separate office and store shall be provided for full time use by the station dealer. Equally,
separate sanitary amenities shall be provided for the station staff to the satisfaction of the
Architect and local authorities.
C | TELEPHONE
The Contractor shall provide a telephone connection to the town exchange for the period of
the Works, and shall pay all fees and rental for the same. The telephone connection shall
remain on site until completion of the works.
D | SANITATION
The Contractor shall make arrangements for the necessary toilet facilities for their staff and
workmen to the requirements and satisfaction of the Health authorities and maintain the same
in a thoroughly clean and sanitary condition and pay all conservancy fees during the period of
the Works and remove when no longer required.
E | PLANT, TOOLS AND SCAFFOLDING
The Contractor shall provide all necessary hoists, tackle, plant, vehicles, tools and appliances
of on every description for the due and satisfactory completion of the Works and shall remove
same completion.
The Contractor shall provide, erect and maintain all temporary scaffolding, sufficiently strong
and efficient for the due performance of the Works, including Sub-contract Works, provide
special scaffolding as and when required during the Works and remove on completion and
make good.
Such scaffolding shall be constructed of tubular steel or timber of sufficient scantlings and be
provided with planked footways and guard-rails to approval.
All such plant, tools and scaffolding shall comply with all regulations whether general or local, in
force throughout the period of the Contract and shall be altered or adapted during the Contract
as may be necessary to comply with any amendments in or additions to such regulations.
Scaffolding is not measured hereinafter, and the Contractor must allow here or in his rates for
| the above. | [7 empty] | 0
[5 empty] | Carried To Collection |  |  | US$ | 0
A | EXISTING AND ADJACENT PROPERTY
The Contractor must take all steps necessary to safeguard existing and adjacent property,
make good at their own expense any damage to persons or property caused thereon, and
hold the Employer indemnified against any such claim arising.
The Contractor will be held fully responsible for the safety of the existing and adjacent buildings
and for any damage caused in consequence of these Works. They must reinstate all damages
at his own expense and indemnify the Employer against any loss.
The Contractor must take such steps and exercise such care and diligence as to minimize
nuisance from dust, noise or any other cause to the occupiers of the existing and adjacent
property.
B | HOARDING
The Contractor shall enclose the site areas under which work is carried out, with
1.80 meter high barbed wire fence comprising treated blue gum poles at centres not
exceeding 3.0meters and 6No barbed wire strands at equal spacing
The contractors attention is drawn to the fact that some areas of the site are
already built up and shall be in use during the currency of this project. As such
the contractor must allow for keeping his/her employees from interfering with
such other users and preventing and minimizing any nuisance arising from dust,
noise or by way of trespass.
Allow for Provisional length of 100 meters @ (tenderer to insert rate and extend)
B | WATCHING AND LIGHTING
The Contractor shall provide at their risk and cost all watching and lighting as necessary to
| safeguard the Works, plant and materials against damage and theft. | [7 empty] | 0
C | SIGNBOARD
The Signboard and lettering on same for the display of the General and Sub-Contractors'
names shall be of an approved size with the Employer's name painted thereon. The Architect's
Quantity Surveyor's and other Consultants' names shall be printed in 50 mm letters all to the
Architect's approved design. No other signboard or advertising will be permitted without prior
| permission from the Architect. | [7 empty] | 0
[5 empty] | Carried To Collection |  |  | US$ | 0
A | PRIME COST RATES
Where description of items include a P.C. rate per unit this rate is to cover the net supply
cost of the unit only. The Contractor's price must include for the cost of the unit at the rate
stated, plus waste, taking delivery, storage, fixing in position, profit and overheads.
The actual net cost per unit will be adjusted within the Final Account against the P.C. rate
stated.
PROTECTION AND CLEANING
B | PROTECTION
The Contractor shall cover up and protect from damage, including damage from inclement
weather, all finished work and unfixed materials, including that of Sub-Contractors, etc., to the
satisfaction of the Architect until the completion of the Contract.
C | CLEANING
The Contractor shall, upon completion of the Works, at their own expense, remove and clear
away all surplus excavated materials, plant, rubbish and unused materials and shall leave the
whole of the Site and Works in a clean and tidy state to the satisfaction of the Architect,
including clearing away and making good all traces of temporary access roads, offices, sheds,
camps, etc. Particular care shall be taken to leave clean all floors and windows and to remove
all paint and cement stains. They shall also, at the discretion of the Architect, remove all
| rubbish and dirt as it accumulates. The Contractor is to find their own dump and shall pay | [7 empty] | 0
all charges in connection therewith.
[5 empty] | Carried To Collection |  |  | US$ | 0
Collection
|  | Brought forward from Page |  |  |  | 1/4 |  |  | 0
|  | Brought forward from Page |  |  |  | 1/5 |  |  | 0
|  | Brought forward from Page |  |  |  | 1/6 |  |  | 0
|  | Brought forward from Page |  |  |  | 1/7 |  |  | 0
|  | Brought forward from Page |  |  |  | 1/8 |  |  | 0
|  | Brought forward from Page |  |  |  | 1/9 |  |  | 0
|  | Brought forward from Page |  |  |  | 1/10 |  |  | 0
|  | Brought forward from Page |  |  |  | 1/11 |  |  | 0
| TOTAL FOR SECTION 1: PRELIMINARIES AND GENERAL DESCRIPTIONS CARRIED TO GRAND SUMMARY | [5 empty] | US$ |  | 0

## PITCH
Item | Description of Work/Items | Project Schedules Ref. | Unit | Qntty | Rate | Amount
GRANT No. KIS065
PROPOSED LUUQ FOOTBALL FIELD
LUUQ, GEDO SOMALIA
ELEMENT 2: FOOTBALL PITCH
SUB STRUCTURES
Earthwork schedules
A | Allow for grading of the existing surface of the pitch including clearing, importing of suitable materials for section with depressions and compact to engineer's satisfaction |  | Item | 1 | 0 | 0
B | Provision of approved painting to pitch marking to Engineer's Approval as per drawing |  | Lsum | 1 | 0 | 0
GOAL POSTS
C | Supply and fix struts/ braces of 100mm dia. CHS section of 5mm thick, with lock on synthetic net hooks, sockets caps, and wedgets bolted thoughout and painted with gloss white paint to finish; dimensios to FIFA standard and Engineers approval |  | No. | 2 | 0 | 0
CORNER DELINATORS
D | Supply corner markers for 4 sides with sockets for fitting at 4 corners of the pitch comprising grouting of 25mm dia. Pipe. dimensios to FIFA standard and Engineers approval |  | No. | 4 | 0 | 0
Total for Pich Ground- BLOCK D | [5 empty] | 0

## SPECTATOR STAND 1
Item | Description of Work/Items | Project Schedules Ref. | Unit | Qntty | Rate | Amount
GRANT No. KIS065
PROPOSED LUUQ FOOTBALL FIELD
LUUQ, GEDO SOMALIA
SECTION 3: SPECTATOR STANDS 1
SUB STRUCTURES
Earthwork schedules
A | Excavation (any soil type) for foundation.This item includes all excavations, disposal and temporary support or shoring if needed. See drawing and schedule for details. |  | CM | 8.76 | 0 | 0
| Construct 400mm thick 500mm high of stone wall foundation for 3.no spectator stands |  | CM | 11.88 | 0 | 0
B | Soil backfilling, gravel with hardcore compaction on stone foundation walling up to 400 mm thick. This includes supplying of needed materials. See drawings and schedules for levels/dimensions and details. |  | CM | 32.13 | 0 | 0
Concrete
Plain concrete class 15/40 OR mix (1:4:8)
D | 50mm Thick blinding to strip foundations |  | CM | 3.57 | 0 | 0
SUB-TOTAL FORWARDED TO NEXT PAGE | [5 empty] | 0
Item | Description of Work/Items |  | Unit | Qntty | Rate | Amount
SUB-TOTAL BROUGHT FROM PREVIOUS PAGE | [5 empty] | 0
SUBTOTAL FOR SUBSTRUCTURES | [5 empty] | 0
FINISHES
External Wall finishes
Cement and sand (1:4) render: on hollow block: steel trowel finished: to
O | 15mm thick:concrete: externally |  | SM | 25.44 | 0 | 0
Prepare surfaces and apply undercoat and two finishing coats first grade emulsion paint on hollow concrete wall surfaces: to
P | Hollow concrete wall: externally |  | SM | 25.44 | 0 | 0
Floor finishes
Q | Cement and sand (1:4) screed: to floors: in
R | 32mm thick finished floor finish |  | SM | 35.7 | 0 | 0
| Allow for Steel railing blustrades at the sides |  | No | 2 | 0 | 0
| SUBTOTAL FOR FINISHES |  |  |  |  | 0
Summary for Spectator Stand 1
1 | Subtotal for Sub structure |  |  |  |  | 0
3 | Subtotal for Finishes |  |  |  |  | 0
Total for Spectator Stand 1 | [5 empty] | 0

## SPECTATOR STAND 2
Item | Description of Work/Items | Project Schedules Ref. | Unit | Qntty | Rate | Amount
GRANT No. KIS065
PROPOSED LUUQ FOOTBALL FIELD
LUUQ, GEDO SOMALIA
SECTION 3: SPECTATOR STANDS 2
SUB STRUCTURES
Earthwork schedules
A | Excavation (any soil type) for foundation.This item includes all excavations, disposal and temporary support or shoring if needed. See drawing and schedule for details. |  | CM | 17.28 | 0 | 0
| Construct 400mm thick 500mm high of stone wall foundation for 3.no spectator stands |  | CM | 25.06 | 0 | 0
B | Soil backfilling, gravel with hardcore compaction on stone foundation walling up to 400 mm thick. This includes supplying of needed materials. See drawings and schedules for levels/dimensions and details. |  | CM | 73.71 | 0 | 0
Concrete
Plain concrete class 15/40 OR mix (1:4:8)
D | 50mm Thick blinding to strip foundations |  | CM | 8.19 | 0 | 0
SUB-TOTAL FORWARDED TO NEXT PAGE | [5 empty] | 0
Item | Description of Work/Items |  | Unit | Qntty | Rate | Amount
SUB-TOTAL BROUGHT FROM PREVIOUS PAGE | [5 empty] | 0
SUBTOTAL FOR SUBSTRUCTURES | [5 empty] | 0
FINISHES
External Wall finishes
Cement and sand (1:4) render: on hollow block: steel trowel finished: to
O | 15mm thick:concrete: externally |  | SM | 64.8 | 0 | 0
Prepare surfaces and apply undercoat and two finishing coats first grade emulsion paint on hollow concrete wall surfaces: to
P | Hollow concrete wall: externally |  | SM | 64.8 | 0 | 0
Floor finishes
Q | Cement and sand (1:4) screed: to floors: in
R | 32mm thick finished floor finish |  | SM | 81.9 | 0 | 0
| Allow for Steel railing blustrades at the sides |  | NO | 2 | 0 | 0
| SUBTOTAL FOR FINISHES |  |  |  |  | 0
Summary for Spectator Stand 2
1 | Subtotal for Sub structure |  |  |  |  | 0
3 | Subtotal for Finishes |  |  |  |  | 0
Total for Spectator Stand 2 | [5 empty] | 0

## FENCE WALL
Item | Description of Work/Items | Project Schedules Ref. | Unit | Qntty | Rate | Amount
GRANT No. KIS065
PROPOSED LUUQ FOOTBALL FIELD
LUUQ, GEDO SOMALIA
SECTION 4: FENCE WALL
SUBSTRUCTURE AND SUPERSTRUCTURE
C | Excavate foundation trenches, 600mm wide and 800mm deep |  | CM | 254.4 | 0 | 0
D | Construct foundation rubble stone 500mm wide and 1000mm high, bedded and jointed with cement mortar 1:3 |  | CM | 169.6 | 0 | 0
E | Construction of RCC Grade beam above foundation walling 400mm wide and 200mm thick, reinforced with 4Y10 bars, and Y8 links @ 200mm C/C spacing. |  | CM | 42.4 | 0 | 0
F | Construct 200mm thick hollow block walls bedded and jointed 1:3 cement ratio. |  | SM | 1378 | 0 | 0
G | Construct 400x200mm thick 3000 mm high hallow block as column pillars starting from ground beam |  | SM | 232.96 | 0 | 0
I | Plaster: 9mm first coat of cement/lime/sand (1:2:9): 3mm second coat of cement/lime/sand (1:1:6): steel trowelled: on masonry or concrete: to both external and internal faces and column pillars |  | SM | 2988.96 | 0 | 0
J | Prepare & apply one coat of white wash, and one coat of emulsion paint on plastered hollow block concrete surfaces: to external and internal faces |  | SM | 2988.96 | 0 | 0
GATES
K | Supply and fix double leaf steel gate size 5000x 2100mm high with small pedestrian door made from 3mm thick steel plate welded on both sides of the frame. Frame as follows: 75x50x3mm thick RHS external members and 25mm SHS 3mm thick secondary members, fixed onto the concrete columns using heavy duty steel pin hinges; with all fastening accessories including all cutting welding, grinding and priming with one coat of grey oxide before fixing. The gate should also have peep holes of not more that 25mm dia with a sliding door. It should also have 2 locking mechanisms, top and bottom. The works will include two support columns and all finishes. |  | No. | 2 | 0 | 0
TOTAL FOR FENCE WALL | [5 empty] | 0

## GRAND SUMMARY
ITEM NO. | DESCRIPTION | PAGE | AMOUNT (US$)
GRANT No. KIS065
PROPOSED LUUQ FOOTBALL FIELD
LUUQ, GEDO SOMALIA
ELEMENT 5: GRAND SUMMARY
1 | SECTION 1: PRELIMINARIES AND GENERAL DESCRIPTIONS |  | 0
2 | SECTION 2: PITCH |  | 0
3 | SECTION 3: SPECTATOR STAND 1 |  | 0
4 | SECTION 4: SPECTATOR STAND 2 |  | 0
5 | SECTION 5: FENCE WALL |  | 0
| TOTAL AMOUNT CARRIED TO FORM OF TENDER | US$ | 0
SIGNED:
(CONTRACTOR) ……………………………………………………………………………………………………………………
Address: ………………………………………………………………………………………………………………………………………
Tel No: ………………………………………………………………………………………………………………………………………
Date: ……………………………………………………………………………………………………………………………………………
SIGNED:
(EMPLOYER ) …………………………………………………………………………………………………………………………
Address: ……………………………………………………………………………………………………………………………………
Tel No: ………………………………………………………………………………………………………………………………………
Date: ………………………………………………………………………………………………………………………………………….